# Tenderloin Improvement Project

Vision: A safer Tenderloin neighborhood with significantly reduced crime and sidewalk hazards and increased investments in long-term neighborhood community resources that promote neighborhood safety and pride.

Strategy:  Convene an operational team of city and non-city organizations that will work to:

- Decrease drug-related crime

- Decrease waste and debris

- Increase cleanliness

- Improve physical environment

# Roles and Responsibilities:

Policy Direction by Mayor’s Office

Strategy by Mayor’s Office, DEM, and community stakeholders

Operational Coordination by DEM

Operations by DPH, HSH, DPW, OEWD, SFPD, SFFD, and community stakeholders

# Success Metrics:

Short-term successes to achieve by February 2022

- Less open drug dealing

- Less open-air drug use

- Fewer tents

- Less trash and waste on sidewalks/streets

- Fewer 911 medical calls to the area

- Fewer 911 violent crime calls to the area

- Increased cleanliness on sidewalks/streets

- Increased feelings of public safety

- Increased police presence out of cars

- Increased coordination with neighborhood and community members

Long-term successes to achieve by December 2022

- Level of safety, cleanliness, etc. achieved is able to be maintained through regular resource allocations from city and neighborhood

  - Fewer fatal and non-fatal overdoses

- Joint feelings of ownership of and dedication to the neighborhood

  - Block parties, Clean Team events, other neighborhood events

  - Community-driven campaign to increase neighborhood pride

  - Increased organizational capacity of TLCBD and other orgs

- Long-term behavior change

  - Visitors and daytime street population have greater awareness of surroundings (less walking into traffic, less lying in streets and sidewalks, clothed appropriately for weather, etc.)

  - Residents and community members feel safe when going out

  - Clear process for residents, CBOs, merchants, city to address neighborhood issues together

- Permanent environmental changes

  - Revamped/expanded yellow brick road of safe passage between school and home for school-aged children

  - Increased nighttime lighting on streets and storefronts

  - Additional positive activations and clean open space

  - Street engineering on identified blocks to slow down/prevent vehicle traffic

# Operational Plan:

Phase 1: Assess (November 2021)

- Convene trusted city partners and community leaders to inform problem statements and operational strategy

- Perform neighborhood assessments to validate Phase 2 Priority Problem Matrix

- Identify existing initiatives and resources in target areas

- Perform initial resource gap analysis

- Finalize and agree upon operational strategy

Phase 2: Crisis Operations (December 2021 – January 2022)

- Weekly coordination meetings to establish and affirm objectives

- Daily operational meetings to confirm priorities and daily tactics

- Coordinate with residents, community partners, and neighborhood organizations to implement tactics that support lasting change

Phase 2 Priority Problem Matrix

| Priority Problem | Lead City Agency | Support Agencies | Possible Solutions |
| --- | --- | --- | --- |
| - Drug dealing and violent crime | SFPD | SFFD DAT DPH | - Infrastructure modifications (trash cans, light poles) - Street engineering |
| - Open air drug use | DPH | HSH SFFD SFPD | - Safe consumption site - Day drop in center / 24 hour behavioral health referral center - Street / sidewalk engineering |
| - Safe passage and accessibility | OEWD | DEM HRC | - Coordination of ambassador programs - Infrastructure modifications and fixes - Yellow brick road project - Dodge Alley activation |
| - Waste and debris | DPW | DPH | - Targeted and frequent cleanings - Increased trash cans / adjusted trash pickups |
| - Housing, shelter, drop-in resources | HSH | DPH | - Identify TL-assigned beds within system of care - Behavioral and mental health resource support |
| - High levels of 911 medical calls | SFFD | DEM DPH | - Coordination with Street Wellness team (start Jan 2022) |
| - Illegal resale / vending | SFPD | DPH DPW DEM | - Outreach and engagement in-language - Environmental health education and enforcement for illegal vending of food - DPW and SFPD coordinated enforcement |

Phase 3: Sustained Operations (February 2022 and onward)

- Secured long-term funding for ambassador programs

- City investments in environmental / space changes

- Ongoing HOT, SFPD, DPW investment

- Facilitate block level community activations

  - Regular block parties and Clean Team events

  - Pop-up art and culture fairs

  - Increased recreation and open space